## Sheet1
FMEA DataRasov Morroco:
Category (5M) | Failure Mode | Cause of Failure | Effects of Failure | Severity | Occurrence | Detectability | RPN | Proposed Action | Responsible
Method | Non-compliance with laws | Lack of knowledge of local laws, especially IT | Project delays, fines, or shutdown | 9 | 6 | 3 | 162 | Hire a legal expert and collaborate with local authorities | Legal Team
Method | Delayed approvals for permits | Bureaucratic delays in local government | Delay in construction and operational launch | 8 | 7 | 4 | 224 | Establish early contact with local government officials | Project Manager
Machine | Power outages | Unreliable local power grid | Downtime, service interruptions | 8 | 5 | 4 | 160 | Install backup power systems (generators, UPS) | Technical Lead
Machine | Cooling system failure | Poor climate control and infrastructure setup | Hardware damage, overheating, interruptions | 9 | 4 | 3 | 108 | Implement a cooling system with redundancy | Facilities Manager
Machine | Hardware failures | Lack of maintenance or poor-quality hardware | Downtime, increased costs | 8 | 6 | 5 | 240 | Regular hardware inspections, implement proactive maintenance schedules | IT Infrastructure Lead
Machine | Natural disasters | Earthquakes, floods, storms | Service disruption, physical damage | 9 | 4 | 6 | 216 | Develop disaster recovery plans, secure insurance, and build resilient facilities | Facilities Manager
Machine | Network connectivity issues | Poor local internet infrastructure, insufficient bandwidth | Slow service, degraded performance | 7 | 7 | 5 | 245 | Partner with multiple ISPs, install backup connections | IT Infrastructure Lead
Man | Insufficient skilled workforce | Lack of training programs and recruitment for local talent | Delayed deployment and project delays | 8 | 6 | 5 | 240 | Partner with local universities for talent development | HR & Recruitment Team
Man | High employee turnover | Uncompetitive salaries, poor working conditions | Loss of continuity, knowledge gaps | 7 | 5 | 6 | 210 | Offer competitive salaries, create retention programs | HR Team
Measurement | Data breach | Insufficient security protocols, lack of encryption | Loss of customer trust, legal issues | 10 | 4 | 5 | 200 | Implement strong encryption, regular security audits | Security Specialist
Man | Insider threats | Lack of employee vetting, poor access control | Unauthorized access, damage to reputation | 9 | 5 | 5 | 225 | Implement strict access controls, employee monitoring | Security Specialist
Machine | Data loss | Lack of backup systems and recovery protocols | Loss of critical data, downtime | 9 | 6 | 3 | 162 | Establish comprehensive disaster recovery and backup plans | Technical Lead
Material | Delayed hardware delivery | Shipping delays, vendor issues | Project delay, inability to meet deadlines | 6 | 7 | 4 | 168 | Partner with multiple suppliers, build buffer stock | Procurement Manager
Man | Misalignment with local culture | Lack of understanding of local market needs | Reduced adoption rates, customer dissatisfaction | 8 | 5 | 5 | 200 | Conduct market research, adapt offerings to local culture | Marketing Team
Man | Language barriers | Language diversity in the region | Miscommunication, poor customer experience | 7 | 6 | 5 | 210 | Hire multilingual staff, translate key materials | HR Team
Method | Inefficient resource allocation | Poor project planning and tracking | Project delays, underutilization or overuse | 8 | 6 | 4 | 192 | Use project management tools (Gantt charts, etc.) | Project Manager
Method | Lack of operational continuity during transition | Poor transition planning between teams | Service downtime, client dissatisfaction | 7 | 7 | 3 | 147 | Create a detailed handover plan for all teams | Project Manager
Machine | Software compatibility issues | Incompatibility of legacy systems | Delayed rollout, increased cost | 6 | 5 | 4 | 120 | Conduct thorough testing with all involved systems | Technical Lead
Machine | Failure of cloud platform | Bugs in platform, software incompatibilities | Service unavailability, customer dissatisfaction | 9 | 5 | 5 | 225 | Test platform thoroughly, ensure robust support contracts | IT Infrastructure Lead
Man | Worker transport delays | Traffic congestion, poor transport options | Reduced productivity, project delays | 8 | 6 | 4 | 192 | Provide employee shuttles, subsidize public transport options, and create flexible work hours | HR & Operations Team