## Tangier Data Center Constructio
Task Name | Start Date | Due Date | Dependencies | Duration (Days) | Baseline Start | Baseline Finish | Variance | Predecessors | Duration
Project Management | 2024-11-14 | 2024-12-03 |  | 5 | 2024-11-24 | 2025-01-05 | 23j |  | 14j
Scheduling | 2024-11-14 | 2024-11-19 |  | 5 | 2024-11-24 | 2024-12-07 | 13j |  | 4j
Stakeholder Engagement | 2024-11-22 | 2024-11-25 | Scheduling | 5 | 2024-12-08 | 2024-12-22 | 19j |  | 2j
Procurement Management | 2024-11-26 | 2024-11-29 | Stakeholder Engagement | 5 | 2024-12-23 | 2025-01-05 | 25j |  | 4j
Financial Oversight | 2024-11-30 | 2024-12-03 | [6 empty] | 3j
Requirements Definition | 2024-12-04 | 2025-01-02 | Project Management | 10 | 2025-01-06 | 2025-01-19 | 11j |  | 22j
Business Requirements | 2024-12-14 | 2024-12-23 |  | 5 | 2025-01-06 | 2025-01-10 | 13j |  | 7j
Technical Requirements | 2024-12-24 | 2025-01-02 | Business Requirements | 5 | 2025-01-11 | 2025-01-19 | 11j |  | 8j
Design and Planning | 2025-01-03 | 2025-01-31 | Requirements Definition | 20 | 2025-01-20 | 2025-02-16 | 10j |  | 21j
Architectural Design | 2025-01-20 | 2025-02-03 |  | 10 | 2025-01-20 | 2025-02-02 | -1j |  | 11j
Cooling System Design | 2025-02-03 | 2025-02-17 | Architectural Design | 10 | 2025-02-03 | 2025-02-16 | -1j |  | 11j
Risk Management (FMECA) | 2025-02-06 | 2025-02-18 | [6 empty] | 9j
Land Acquisition & Permits | 2025-02-18 | 2025-04-21 | Design and Planning | 20 | 2025-02-17 | 2025-03-15 | -26j |  | 45j
Locating Suitable Land | 2025-02-17 | 2025-03-03 |  | 10 | 2025-02-17 | 2025-03-01 | -1j |  | 11j
Purchasing the Land | 2025-03-02 | 2025-03-10 | Locating Suitable Land | 5 | 2025-03-02 | 2025-03-08 | -1j |  | 7j
Acquiring Land Papers | 2025-03-09 | 2025-03-17 | Purchasing the Land | 5 | 2025-03-09 | 2025-03-15 | -1j |  | 7j
Building Permits | 2025-03-16 | 2025-03-24 | Acquiring Land Papers | 10 |  |  |  |  | 7j
Construction | 2025-04-20 | 2025-11-17 | Land Acquisition & Permits | 90 | 2025-03-16 | 2025-07-26 | -81j |  | 152j
Site Preparation | 2025-03-16 | 2025-03-31 |  | 15 | 2025-03-16 | 2025-03-30 | -1j |  | 12j
Building Construction | 2025-03-31 | 2025-06-13 | Site Preparation | 60 | 2025-03-31 | 2025-06-27 | 9j |  | 55j
Security and Accessibility | 2025-05-28 | 2025-06-12 | Building Construction | 15 | 2025-06-28 | 2025-07-12 | 21j |  | 12j
Renewable Energy Grid Connection | 2025-05-28 | 2025-06-11 | [6 empty] | 11j
Water Supply Systems | 2025-06-12 | 2025-07-18 | [6 empty] | 27j
Cooling and Power Systems | 2025-06-22 | 2025-07-18 | [6 empty] | 21j
Health and Safety Compliance | 2025-07-20 | 2025-07-28 | [6 empty] | 7j
Backp Power Systems | 2025-09-18 | 2025-12-08 | [6 empty] | 58j
Installing Backup Power Systems | 2025-07-20 | 2025-07-25 | [6 empty] | 6j
Testing bckup systems | 2025-07-26 | 2025-08-01 | [6 empty] | 6j
Sewer and Waste Management | 2025-12-09 | 2026-01-19 | Overlaps with Construction | 4 | 2025-03-30 | 2025-04-27 | -191j |  | 30j
Sewer Connection Design | 2025-03-30 | 2025-04-07 |  | 7 | 2025-03-30 | 2025-04-06 | -1j |  | 7j
Sewer Connection Installation | 2025-04-07 | 2025-04-17 | Sewer Connection Design | 10 | 2025-04-07 | 2025-04-17 | -1j |  | 9j
Sewer Connection Testing | 2025-04-18 | 2025-04-28 | Sewer Connection Installation | 10 | 2025-04-18 | 2025-04-27 | -1j |  | 7j
Waste Management | 2025-04-28 | 2025-12-19 | Sewer Connection Testing | 4 |  |  |  |  | 170j
Acquisition | 2025-12-19 | 2026-01-08 | Construction | 2 | 2025-07-28 | 2025-08-10 | -109j |  | 15j
Site Contracts | 2025-07-28 | 2025-08-04 |  | 5 | 2025-07-28 | 2025-08-03 | -1j |  | 6j
Hardware Procurement | 2025-08-04 | 2025-08-11 | Site Contracts | 7 | 2025-08-04 | 2025-08-10 | -1j |  | 6j
Communication Services | 2025-08-11 | 2026-01-08 | Hardware Procurement | 7 | 2025-08-11 | 2025-08-18 | -104j |  | 109j
Software Design, Installation, and IT Infrastructure | 2026-01-09 | 2026-05-08 | Acquisition | 20 | 2025-08-11 | 2025-09-05 | -176j |  | 86j
System Integration | 2025-08-11 | 2025-08-18 |  | 7 | 2025-08-11 | 2025-08-18 | -1j |  | 6j
IT Infrastructure Deployment | 2025-08-19 | 2025-08-28 | Software Design | 10 | 2025-08-19 | 2025-08-28 | -1j |  | 8j
Software Testing | 2025-09-06 | 2026-05-08 | System Integration | 7 | 2025-09-06 | 2025-09-12 | -171j |  | 176j
Operations Setup | 2026-05-09 | 2026-07-08 | Software Design, Installation, and IT Infrastructure | 3 | 2025-09-06 | 2025-09-26 | -204j |  | 44j
Workforce Recruitment | 2025-09-06 | 2025-09-12 |  | 7 | 2025-09-06 | 2025-09-12 | -1j |  | 6j
Energy Optimization | 2025-09-13 | 2025-09-19 | Workforce Recruitment | 7 | 2025-09-13 | 2025-09-19 | -1j |  | 6j
Security Operations | 2025-09-20 | 2026-05-08 | Energy Optimization | 7 | 2025-09-20 | 2025-09-26 | -161j |  | 166j
Testing and Commissioning | 2026-06-09 | 2026-09-22 | Operations Setup | 15 | 2025-09-27 | 2025-10-17 | -243j |  | 76j
System Testing | 2025-09-27 | 2025-10-06 |  | 7 | 2025-09-27 | 2025-10-05 | -1j |  | 7j
Compliance Checks | 2025-10-06 | 2025-10-13 | System Testing | 7 | 2025-10-06 | 2025-10-12 | -1j |  | 6j
Operational Continuity | 2025-10-13 | 2025-10-17 | Compliance Checks | 5 | 2025-10-13 | 2025-10-17 | -1j |  | 5j
Final Risk Assessment | 2025-10-18 | 2026-09-22 | Operational Continuity | 5 |  |  |  |  | 243j
Post-Handover Support | 2026-09-23 | 2026-12-11 | Testing and Commissioning | 10 | 2025-10-18 | 2025-10-31 | -291j |  | 58j
Documentation | 2025-10-18 | 2025-10-24 |  | 5 | 2025-10-18 | 2025-10-24 | -1j |  | 6j
Technical Support | 2025-10-25 | 2025-10-31 | Documentation | 5 | 2025-10-25 | 2025-10-31 | -1j |  | 6j
Regular Maintenance | 2025-10-25 | 2025-10-31 | Technical Support | 5 | 2025-10-25 | 2025-10-31 | -1j |  | 6j
Performance Monitoring | 2025-10-25 | 2025-10-31 | Regular Maintenance | 5 | 2025-10-25 | 2025-10-31 | -1j |  | 6j
Stakeholder Communication | 2025-10-25 | 2026-12-11 | Performance Monitoring | 5 | 2025-10-25 | 2025-10-31 | -291j |  | 296j